## Project Overview
Project Detail | Information
Project Name | AI Financial Roaster (Zero-Cost Dev Stack)
Project Scope | A personality-driven expense analyzer utilizing Gemini AI
Total Timeline | 15 Working Days (3 Weeks)
Critical Rule | If stuck on an error for >60 minutes, explicitly ask for help.

## Week 1 - Foundation
Task ID | Task Description (A-Z Steps) | Expected Output / Definition of Done | Timeline | Assignee | Status
1.1 | Workspace Setup: Initialize a GitHub Repository (add .gitignore for Node). Set up a Task tracker sheet to track all tasks below. | Repo exists; Task tracker sheet - Ready to use. | Day 1 |  | To Do
1.2 | Supabase DB Setup: Create a free Supabase project. Create an Expenses table with columns: id, amount, category, description, created_at. | Table is live and accessible via the Supabase dashboard. | Day 1 |  | To Do
1.3 | Backend Initialization: Initialize a Node.js project (npm init). Install Express, dotenv, and the Supabase JavaScript client. | A running server.js file logging 'Server running on port 3000'. | Day 2 |  | To Do
1.4 | Create CRUD Endpoints: Write a POST /api/expenses route to add an expense to Supabase, and a GET /api/expenses route to retrieve them. | Code written and successfully connecting to Supabase. | Day 3 |  | To Do
1.5 | API Testing: Use Postman to test both endpoints. Ensure adding dummy data through Postman shows up in Supabase. | Postman screenshots showing successful 200 OK responses. | Day 4 |  | To Do
1.6 | Buffer & Debugging: Interns will likely face environment variable (.env) issues or basic syntax errors. Use this day to debug and finalize the backend. | Clean, working, documented backend code. | Day 5 |  | To Do

## Week 2 - AI & UI
Task ID | Task Description (A-Z Steps) | Expected Output / Definition of Done | Timeline | Assignee | Status
2.1 | Gemini API Setup: Generate a free API key from Google AI Studio. Store it securely in the backend .env file. Never commit this to GitHub. | Key is generated and secured. | Day 6 |  | To Do
2.2 | AI Logic Integration: Create a POST /api/roast endpoint. Pass the week's expenses to Gemini with a strict system prompt instructing it to be humorous and financially strict. | Postman returns a funny, contextual AI response based on dummy data. | Day 7 |  | To Do
2.3 | Frontend Initialization: Use Vite to scaffold a React app (npm create vite@latest). Install Tailwind CSS for styling. | React default page loads successfully on localhost:5173. | Day 8 |  | To Do
2.4 | UI Layout - Input Form: Build a clean, mobile-friendly form with inputs for Amount, Category (Dropdown), and Description. | UI form is visible and looks presentable (doesn't need to work yet). | Day 9 |  | To Do
2.5 | UI Layout - History & Roast: Build a list view below the form to show past expenses, and a dedicated 'Card' at the top to display the AI Roast. | Static UI components are fully built. | Day 10 |  | To Do

## Week 3 - Wiring & Launch
Task ID | Task Description (A-Z Steps) | Expected Output / Definition of Done | Timeline | Assignee | Status
3.1 | Frontend to Backend Connection: Use fetch or axios in React to send form data to the POST /api/expenses backend endpoint. | Typing in the React UI successfully saves data to Supabase. | Day 11 |  | To Do
3.2 | Fetching the Roast: Add a button in React saying 'Analyze My Spend'. When clicked, it calls the POST /api/roast endpoint and displays the AI text on screen. | The app is fully functional end-to-end locally. | Day 12 |  | To Do
3.3 | CORS & Error Handling: Fix Cross-Origin Resource Sharing (CORS) errors between frontend/backend. Add loading states (spinners) while waiting for the AI to respond. | No console errors; smooth user experience. | Day 13 |  | To Do
3.4 | Deployment: Deploy the Node.js backend to Render. Deploy the React Vite frontend to Vercel. Ensure environment variables are added to both platforms. | Two live URLs (Frontend app, Backend API). | Day 14 |  | To Do
3.5 | Final QA & Demo Prep: Test the live URL on mobile phones. Fix any mobile layout squishing. Prepare a 5-minute presentation demonstrating the live app. | Project signed off and ready to show. | Day 15 |  | To Do